## Slide 1: Project Name: status report
[Date] | [Project manager]

## Slide 2: Summary
Schedule
On track
Budget
At risk
Scope
On track
Quality
Needs attention
In one sentence: where the project stands, and the one thing the reader must know.
Green is on track, amber is at risk, red needs a decision.

## Slide 3: Progress this period
Finished: the design was signed off by the steering group
Finished: the supplier contract was agreed
Started: building the first release
Next period: test the first release with ten users

## Slide 4: Milestones
Milestone | Due | Status
Design signed off | 15 March | Done
Contract agreed | 30 March | Done
First release built | 30 April | In progress
User testing | 20 May | Not started
Go live | 30 June | Not started

## Slide 5: Budget
Chart: Planned and spent, £ thousand
| Jan | Feb | Mar | Apr | May | Jun
Planned | 40 | 45 | 50 | 55 | 50 | 40
Spent | 38 | 47 | 56 | 61
£202k
spent of £280k, 6% over plan to date.
Why, and what is being done about it.

## Slide 6: Risks and issues
Risk or issue | Impact | Owner | What is being done
Supplier may deliver late | High | [Name] | Weekly check-in; second supplier lined up
Two people leave in May | Medium | [Name] | Handover notes; cover agreed
Testing room not booked | Low | [Name] | Booking this week

## Slide 7: Next steps
Agree the budget change at the next steering group
Finish the first release
Book the user testing sessions